## Slide 1
ABANGCEBU AI / DELIVERY REVIEW
Sprints 1–3
Jira issue/status snapshot • 16 Oct 2026 • Philippines time
01
From foundation and design to the implementation backlog
27/27
Sprint 1 • Done
17/20
Sprint 2 • Done
0/35
Sprint 3 • Done
Status reflects Jira now, not a historical burndown or independent acceptance audit.

## Slide 2
01 / EXECUTIVE VIEW
Three sprints, three different states
Jira snapshot • 16 Oct 2026
02
SPRINT 1 / CLOSED
27 Done / 27
15 Sep–2 Oct planned; closed 1 Oct
SPRINT 2 / ACTIVE
17 Done / 20
1–15 Oct planned; 3 in development
SPRINT 3 / FUTURE
35 Ready / 35
No Jira start or end date recorded
82 sprint issue entries total • all three sprint issue lists reconciled to Jira totals.

## Slide 3
02 / SPRINT 1
Foundation and requirements
Jira snapshot • 16 Oct 2026
03
27 of 27 tickets Done
Project setup, Git collaboration, Next.js/MapLibre direction, Supabase/PostGIS schema and RLS planning.
Design handoff
Personas, roles, identity flows, UI wireframes, test plans and performance strategy prepared for subsequent work.
Jira state: CLOSED • Completed 1 Oct 2026 • Planned end 2 Oct 2026

## Slide 4
03 / SPRINT 2
Detailed flows and validation plans
Jira snapshot • 16 Oct 2026
04
17 of 20 tickets Done
Authentication diagrams and test matrices; landing/map initialization, spatial search, filters and drawer flows; functional specification.
3 tickets in development
SCRUM-125 Landlord listing flows
SCRUM-126 Admin KYC / moderation
SCRUM-127 Renter engagement flows
Jira still marks Sprint 2 ACTIVE beyond its planned 15 Oct end.

## Slide 5
04 / SPRINT 3
Implementation and QA backlog
Jira snapshot • 16 Oct 2026
05
35 of 35 tickets READY
Planned EC2 staging, CI/CD, IAM, monitoring, database/RLS migrations and authentication/RBAC implementation.
Scope ahead
Planned page, map and search UI; AI-assistant design; security, performance and end-to-end testing.
Future sprint; no dates recorded. All 35 tickets assigned to Hermar centillas in Jira.

## Slide 6
05 / CONTINUITY
How the work connects
Jira snapshot • 16 Oct 2026
06
01
SPECIFY
Identity, data, access, UX
02
DETAIL
Module flows, test design
03
BUILD + VERIFY
Implementation, staging, QA
Thematic reading of Jira titles—not a verified dependency graph.

## Slide 7
06 / ATTENTION ITEMS
Risks to resolve before Sprint 3
Jira snapshot • 16 Oct 2026
07
Close Sprint 2 carry-over
SCRUM-125–127 are still IN DEVELOPMENT; SCRUM-161 tracks the handoff.
Confirm acceptance
A Done status is not independent evidence of code, testing or stakeholder acceptance.
Rebalance capacity
35 Sprint 3 tickets currently have one Jira assignee; validate owners, estimates and sequence.
Local audit note: Sprint 2 draft packages were attached; visual/product/schema QA and acceptance remained open.

## Slide 8
07 / DECISIONS
Recommended next actions
Jira snapshot • 16 Oct 2026
08
1 Review and accept carry-over
Verify the three flowchart tickets against the agreed product/schema criteria.
2 Replan Sprint 3
Confirm dates, owners and capacity before starting implementation.
3 Set a verification gate
Require ticket-level code, test and acceptance evidence before calling work delivered.

## Slide 9
08 / SOURCES
Evidence and interpretation
Source retrieval: Jira board #1 • 16 Oct 2026
09
Jira SCRUM board #1: Sprint 1 (#4), Sprint 2 (#70), Sprint 3 (#72).
27 + 20 + 35 sprint issue entries; metadata and issue statuses checked live.
https://abangcebuai.atlassian.net/jira/software/projects/SCRUM/boards/1
Supporting narrative: docs/reports/AbangCebu_Sprints_1-3_Report.docx
Scope: issue/status snapshot, not verified burndown, implementation, test results or acceptance.