## Slide 1
SPRINT 1 → SPRINT 2 → SPRINT 3
What is Done? What is Next?
Abang Cebu AI • ticket-by-ticket Jira status • 16 October 2026
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 1
27 / 27
SPRINT 1 • DONE
17 / 20
SPRINT 2 • DONE
0 / 35
SPRINT 3 • DONE
Jira status is not independent proof of implementation or acceptance.

## Slide 2
SPRINT 1 / CLOSED
27 of 27 tickets Done
15 Sep–2 Oct planned • completed 1 Oct 2026 • foundation, requirements, UX, test plans
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 2
All 27 Sprint 1 issue statuses are Done.
Scope: project setup; database and security design; authentication specifications; wireframes; test and performance planning.

## Slide 3
SPRINT 1 / TICKETS 1
Sprint 1: tickets 1–10
27 / 27 Done • Jira sprint closed
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 3
SCRUM-10
DONE
Create AbangCebu System Flowcharts
SCRUM-49
DONE
Establish Git Branching & PR Collaboration Strategy
SCRUM-6
DONE
create AWS account for the team
SCRUM-55
DONE
Draft Row Level Security (RLS) Policy Specifications
SCRUM-62
DONE
Define Landlord Persona, Permissions & Capabilities
SCRUM-50
DONE
Configure UI Framework & Styling Guidelines
SCRUM-51
DONE
Environment Variables & Secrets Governance Plan
SCRUM-52
DONE
Plan Supabase Project Structure & Extensions
SCRUM-53
DONE
Design Initial Database ERD Diagram
SCRUM-54
DONE
Define Users & Profiles Table Schema Specification

## Slide 4
SPRINT 1 / TICKETS 2
Sprint 1: tickets 11–20
27 / 27 Done • Jira sprint closed
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 4
SCRUM-56
DONE
Specify User Registration Workflow & Data Contract
SCRUM-57
DONE
Specify User Login & Session Token Lifecycle
SCRUM-58
DONE
Specify User Logout & Session Invalidation
SCRUM-60
DONE
Document Authentication Error Handling & Edge Cases
SCRUM-48
DONE
Plan Next.js 15 & MapLibre Project Foundation
SCRUM-64
DONE
Design Landing Page Wireframe / Mockup
SCRUM-63
DONE
Create Role-Based Access Control (RBAC) Matrix
SCRUM-61
DONE
Define Renter Persona, Permissions & Capabilities
SCRUM-59
DONE
Specify Password Reset & Recovery Workflow
SCRUM-65
DONE
Design Login Page Wireframe / Mockup

## Slide 5
SPRINT 1 / TICKETS 3
Sprint 1: tickets 21–27
27 / 27 Done • Jira sprint closed
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 5
SCRUM-66
DONE
Design Registration Page Wireframe / Mockup
SCRUM-67
DONE
Design User Dashboard Wireframe / Mockup
SCRUM-68
DONE
Design Profile Page Wireframe / Mockup
SCRUM-69
DONE
Draft Authentication Test Plan & Test Scenarios
SCRUM-70
DONE
Draft Role & Access Permission Verification Test Cases
SCRUM-71
DONE
Draft Protected Route & Middleware Test Scenarios
SCRUM-72
DONE
Plan Authentication Baseline Latency & Load Strategy

## Slide 6
SPRINT 2 / ACTIVE
17 Done · 3 In Development
1–15 Oct planned • Jira still marks the sprint active as of 16 Oct 2026
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 6
Done: authentication flows and test plans, spatial discovery flows, functional specification.
Not Done: SCRUM-125 landlord; SCRUM-126 admin KYC; SCRUM-127 renter engagement flowcharts.

## Slide 7
SPRINT 2 / TICKETS 1
Sprint 2: tickets 1–10
17 Done • 3 In Development • Jira sprint active
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 7
SCRUM-104
DONE
Sign Up Module & Flowchart: Registration & PKCE Verification
SCRUM-105
DONE
Log In Module & Flowchart: Authentication & Session Token Lifecycle
SCRUM-106
DONE
Password Reset Module & Flowchart: Self-Service Recovery Workflow
SCRUM-107
DONE
Sign Out Module & Flowchart: Session Termination & Multi-Tab Sync
SCRUM-108
DONE
Error Handling & Suspension Module & Flowchart: Failure Taxonomy & UX States
SCRUM-109
DONE
Authentication Master Test Plan & Test Matrix
SCRUM-110
DONE
Sign Up Module Test Plan & Registration Test Cases
SCRUM-111
DONE
Log In Module Test Plan & Session Token Test Cases
SCRUM-112
DONE
Password Reset & Sign Out Module Test Cases
SCRUM-113
DONE
Route Guards & Middleware Security Test Cases

## Slide 8
SPRINT 2 / TICKETS 2
Sprint 2: tickets 11–20
17 Done • 3 In Development • Jira sprint active
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 8
SCRUM-114
DONE
Authentication Baseline Latency & Load Strategy
SCRUM-116
DONE
Landing Page Master Orchestration & Spatial Discovery Flowchart
SCRUM-117
DONE
Sub-Process 2.1: Map Initialization, Viewport & Geolocation Flowchart
SCRUM-118
DONE
Sub-Process 2.2: Spatial Search, Landmark Auto-Suggest & PostGIS Query Flowchart
SCRUM-119
DONE
Sub-Process 2.3: Multi-Criteria Filter Pills & URL State Sync Flowchart
SCRUM-120
DONE
Sub-Process 2.4: Bidirectional Pin Marker & 3-Snap Gesture Drawer Flowchart
SCRUM-122
DONE
FUNCTION SPECIFICATION DOCUMENT FOR ABANG CEBU
SCRUM-125
IN DEV
Module 3: Landlord Onboarding & Listing Management Flowcharts
SCRUM-126
IN DEV
Module 4: Admin KYC Verification & Listing Moderation Flowcharts
SCRUM-127
IN DEV
Module 5: Renter Favorites, Contact & Viewing Inquiry Flowcharts

## Slide 9
SPRINT 3 / FUTURE
35 Ready · 0 Done
No start or end date recorded in Jira • implementation and verification backlog
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 9
Planned: staging and CI/CD; database/RLS; authentication, map and UI; AI design; security and QA.
Ready is a workflow status, not evidence of completed work.

## Slide 10
SPRINT 3 / TICKETS 1
Sprint 3: tickets 1–10
35 Ready • 0 Done • sprint not started
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 10
SCRUM-134
READY
Provision AWS EC2 staging environment for Next.js app
SCRUM-135
READY
Set up GitHub Actions CI pipeline (tsc, lint, build)
SCRUM-136
READY
Automate deployment from main to EC2 staging
SCRUM-137
READY
Define IAM least-privilege roles and policies for staging
SCRUM-138
READY
IAM access review and security audit of staging
SCRUM-139
READY
Set up monitoring, logging and uptime alerts for staging
SCRUM-140
READY
Implement core listing tables migration
SCRUM-141
READY
Implement engagement tables migration (inquiries, saved_listings, reviews, audit_logs)
SCRUM-142
READY
Apply Row Level Security policies as migrations
SCRUM-143
READY
Create PostGIS search functions (viewport bbox and landmark radius)

## Slide 11
SPRINT 3 / TICKETS 2
Sprint 3: tickets 11–20
35 Ready • 0 Done • sprint not started
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 11
SCRUM-144
READY
Seed Metro Cebu landmarks and sample listings
SCRUM-145
READY
Configure Supabase Storage buckets and database backups
SCRUM-146
READY
Complete Database Specification workbook (.xlsx)
SCRUM-147
READY
Implement sign-up and email verification (PKCE)
SCRUM-148
READY
Implement login, session refresh and Remember Me
SCRUM-149
READY
Implement logout and multi-tab sign-out sync
SCRUM-150
READY
Implement password reset and recovery
SCRUM-151
READY
Implement RBAC middleware and route guards
SCRUM-152
READY
Implement standard API error contract and auth error handling
SCRUM-153
READY
Build shared UI component library (Tailwind v4 tokens)

## Slide 12
SPRINT 3 / TICKETS 3
Sprint 3: tickets 21–30
35 Ready • 0 Done • sprint not started
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 12
SCRUM-154
READY
Implement login, registration and password reset pages
SCRUM-155
READY
Implement MapLibre map canvas with Metro Cebu viewport and Locate Me
SCRUM-156
READY
Implement landing page, search bar and landmark auto-suggest
SCRUM-157
READY
Implement filter pills, URL state sync and results drawer
SCRUM-158
READY
Module 6: AI Rental Assistant Flowcharts and Specification
SCRUM-159
READY
Define AI assistant API contract, prompt policy and evaluation set
SCRUM-160
READY
Extend Function Specification Document with Modules 3 to 5
SCRUM-161
READY
Review and close Sprint 2 carry-over (SCRUM-125, 126, 127)
SCRUM-162
READY
Execute authentication test plan against staging
SCRUM-163
READY
Execute RBAC and route guard tests

## Slide 13
SPRINT 3 / TICKETS 4
Sprint 3: tickets 31–35
35 Ready • 0 Done • sprint not started
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 13
SCRUM-164
READY
Browser, mobile and usability testing of auth pages and map UI
SCRUM-165
READY
Write test plans for Modules 3, 4 and 5
SCRUM-166
READY
Execute k6 load tests on staging (steady-state and burst)
SCRUM-167
READY
System test plan and first end-to-end run (auth to map to listing)
SCRUM-168
READY
Sprint 3 review, retrospective and reporting

## Slide 14
SOURCE AND INTERPRETATION
Jira status snapshot
Board 1 • project SCRUM • sprint IDs 4, 70, 72
ABANG CEBU AI • JIRA SNAPSHOT 16 OCT 2026 • 14
82 sprint issue entries: 27 + 20 + 35. Counts reconciled with Jira sprint issue-list totals.
Issue keys on the ticket slides link to Jira. “Done” means the current Jira workflow status only; it is not a code, artifact, test, or acceptance audit.
Source: https://abangcebuai.atlassian.net/jira/software/projects/SCRUM/boards/1/backlog