## TEST DEFINITION
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | AUTHENTICATION & IDENTITY SUBSYSTEM (MODULES 1 TO 5)
| Test Description: |  | Comprehensive QA test specification for User Registration, Login & Sessions, Logout, Password Recovery, and Security Edge Defenses.
| TYPE OF TEST: |  | UT / IT / ST
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
SUBMODULE DIRECTORY & SPECIFICATION SUMMARY
No | Submodule Name | Jira Key | Assigned Engineer | Test Focus | Total Cases | Status
1 | USER REGISTRATION & ACTIVATION | SCRUM-56 | John Lloyd Ando | Input validation, NIST password, PH phone, PKCE activation | 11 | Pending Sprint 2
2 | USER LOGIN & SESSION LIFECYCLE | SCRUM-57 | John Lloyd Ando | Credentials, HTTP-only cookies, RTR rotation, lockout | 8 | Pending Sprint 2
3 | USER SIGN-OUT & INVALIDATION | SCRUM-58 | junrilldisoy90 | Local/global logout, cookie zeroing, multi-tab broadcast | 5 | Pending Sprint 2
4 | PASSWORD RESET & RECOVERY | SCRUM-59 | Joan Marie Encallado Inting | Self-service recovery, anti-enumeration, session revocation | 5 | Pending Sprint 2
5 | AUTH SECURITY & EDGE DEFENSES | SCRUM-60 | junrilldisoy90 | Brute force lockout, suspended account block, CSRF | 7 | Pending Sprint 2
TOTAL TEST SCENARIOS PLANNED |  |  |  |  | 36 | 36 Planned

## ALL_TEST_CASES
No | Test Classification | Test Steps: | Test Confirmation | Test Results
MODULE 1: USER REGISTRATION & ACTIVATION (SCRUM-56) — Assigned: John Lloyd Ando
1 | Registration - Valid Renter | 1. Submit RegisterPayload with valid email, NIST-compliant password, role='renter', and phone '09171234567'. 2. Call registration Route Handler. | 1. HTTP 200/201 response. 2. Phone normalized to canonical +639171234567. 3. Profile row created in public.profiles via handle_new_user() trigger. 4. Verification email sent.
2 | Registration - Valid Landlord | 1. Submit RegisterPayload with role='landlord', valid credentials, and preferred landmark. 2. Execute registration Route Handler. | 1. User created with role='landlord'. 2. Response directs to /landlord/onboarding. 3. Landlord verification entity initialized.
3 | Registration - Anti-Privilege Escalation | 1. Submit payload attempting role='admin'. 2. Validate TypeScript contract, Route Handler validation, and database trigger. | 1. Contract rejects payload with INVALID_ROLE. 2. If bypassed via raw HTTP, server returns HTTP 403 PRIVILEGE_ESCALATION_ATTEMPT. 3. DB trigger enforces fallback to 'renter'.
4 | Registration - Weak Password Rejection | 1. Attempt registration with password < 8 chars ('Ab1!'). 2. Attempt password missing special character ('Password123'). 3. Attempt password exceeding 72 chars. | 1. Request rejected with HTTP 422 WEAK_PASSWORD. 2. Response details specify exact unmet NIST criteria. 3. Zero user records created.
5 | Registration - Invalid Philippine Phone | 1. Attempt registration with non-PH numbers (+1234567890, 08123456789, 12345). | 1. Validation fails with HTTP 422 INVALID_PHONE_NUMBER. 2. Field error explicitly requires 09XXXXXXXXX or +639XXXXXXXXX format.
6 | Registration - Duplicate Email Handling | 1. Submit registration payload using an existing email address (mika.cebu@example.com). | 1. Anti-enumeration defense preserves privacy. 2. Dispatches password reset notification to owner without revealing account collision to scraper.
7 | Registration - Turnstile Bot Defense | 1. Submit registration request with missing or invalid turnstileToken. | 1. Request immediately rejected with HTTP 400 CAPTCHA_VERIFICATION_FAILED. 2. Zero database queries executed.
8 | Email Verification - Valid PKCE Exchange | 1. User clicks confirmation link GET /auth/callback?code=VALID_CODE&type=signup. 2. Route Handler exchanges code via @supabase/ssr. | 1. auth.users.email_confirmed_at timestamp set. 2. Authenticated session cookies issued. 3. Redirects safely to /search (Renter) or /dashboard (Landlord).
9 | Email Verification - Expired Confirmation Code | 1. User clicks confirmation link after 24 hours (code=EXPIRED_CODE). | 1. Route Handler catches Supabase exchange error. 2. Redirects to /login?error=confirmation_expired. 3. UI displays persistent banner with resend CTA.
10 | Email Verification - Tampered PKCE Code | 1. Submit request with corrupted code code=INVALID_12345. | 1. Exchange fails. 2. Redirects to /login?error=invalid_confirmation_link. 3. Zero session cookies issued.
11 | Email Verification - Open-Redirect Defense | 1. User clicks link containing open-redirect injection: ?next=https://attacker-cebu.com. | 1. isSafeRedirectUrl() flags external protocol. 2. Destination sanitized and forced to default internal path (/search).
MODULE 2: USER LOGIN & SESSION LIFECYCLE (SCRUM-57) — Assigned: John Lloyd Ando
12 | Login - Valid Renter Login | 1. Submit valid Renter credentials (mika.cebu@example.com). 2. Execute login Route Handler. | 1. HTTP 200 response. 2. HTTP-only session cookies set (sb-*-auth-token, HttpOnly, Secure, SameSite=lax). 3. Redirect target resolved to /search.
13 | Login - Valid Landlord Login | 1. Submit valid Landlord credentials (carlos.landlord@example.com). | 1. HTTP 200 response. 2. Session cookies set. 3. Redirect target resolved to /dashboard.
14 | Login - Invalid Credentials | 1. Submit valid email with incorrect password. 2. Repeat 3 times. | 1. Request rejected with HTTP 401 AUTH_INVALID_CREDENTIALS. 2. Generic message: 'Invalid email or password.' 3. Zero cookies set.
15 | Login - Unconfirmed Email Block | 1. Attempt login using unconfirmed.renter@example.com. | 1. Request rejected with HTTP 403 AUTH_EMAIL_NOT_CONFIRMED. 2. UI instructs user to verify email before accessing account.
16 | Login - Suspended Account Block | 1. Attempt login with suspended landlord credentials (scammer.landlord@example.com). | 1. Authentication fails with HTTP 403 ACCOUNT_SUSPENDED. 2. Edge Middleware immediately blocks session creation. 3. UI directs user to support contact.
17 | Session - Cookie Chunking (>4096 Bytes) | 1. Authenticate user with extensive profile metadata triggering serialized cookie payload > 4KB. | 1. @supabase/ssr chunks session across sb-*-auth-token.0, sb-*-auth-token.1. 2. Middleware successfully reconstructs session. 3. Zero hydration drops.
18 | Session - Refresh Token Rotation (RTR) | 1. Present active refresh token to obtain fresh 1-hour JWT access token. | 1. New JWT issued. 2. Old refresh token invalidated; new single-use refresh token returned. 3. 30-second concurrency grace period active.
19 | Session - Token Reuse Detection & Lockout | 1. Malicious actor re-submits a previously rotated (revoked) refresh token. | 1. Supabase GoTrue flags token family reuse. 2. Entire token family instantly revoked. 3. All active sessions for user terminated. 4. HTTP 401 AUTH_REFRESH_TOKEN_REUSED emitted.
MODULE 3: USER SIGN-OUT & SESSION INVALIDATION (SCRUM-58) — Assigned: junrilldisoy90
20 | Logout - Local Device Sign-Out | 1. Authenticated user triggers Sign Out. 2. Execute signOutAction({ scope: 'local' }). | 1. Current session deleted in auth.sessions. 2. Set-Cookie emits Max-Age=0 and past epoch for all cookie chunks. 3. Remote sessions on other devices remain active.
21 | Logout - Global Multi-Device Sign-Out | 1. User selects 'Log out of all devices'. 2. Execute signOutAction({ scope: 'global' }). | 1. All rows for user_id purged from auth.sessions. 2. All refresh token families revoked. 3. All sessions across all devices terminated.
22 | Logout - Multi-Tab Broadcast Coordination | 1. User opens Tab A and Tab B while logged in. 2. User clicks Sign Out in Tab A. | 1. Tab A executes logout and posts SIGNED_OUT to BroadcastChannel('supabase.auth.token'). 2. Tab B receives message, purges local cache, and redirects to /login.
23 | Logout - Router Cache Purge & Back Button Guard | 1. User logs out from /dashboard. 2. User clicks browser 'Back' button. | 1. Next.js router.refresh() purges client cache. 2. Protected route headers (Cache-Control: no-store) force server re-evaluation. 3. Middleware blocks access with HTTP 307 to /login.
24 | Logout - Offline Sign-Out Fallback | 1. Disconnect network (navigator.onLine = false). 2. User triggers Sign Out. | 1. Optimistic local cookie destruction executes. 2. Memory credentials flushed. 3. UI navigates safely to unauthenticated state.
MODULE 4: PASSWORD RESET & RECOVERY (SCRUM-59) — Assigned: Joan Marie Encallado Inting
25 | Password Reset - Valid Request | 1. Submit valid email to POST /api/auth/reset-password/request. | 1. HTTP 200 response. 2. Generic message: 'If an account is associated with this email, a recovery link has been dispatched.' 3. Single-use PKCE link sent.
26 | Password Reset - Anti-Enumeration Neutrality | 1. Submit unregistered email (nonexistent.user@example.com). | 1. HTTP 200 response. 2. Message and timing match valid request identically (artificial jitter applied). 3. Zero account existence disclosure.
27 | Password Reset - Rate Limiting | 1. Submit 4 password reset requests within a 15-minute rolling window for the same email. | 1. Requests 1–3 succeed. 2. Request 4 rejected with HTTP 429 AUTH_PASSWORD_RESET_RATE_LIMIT.
28 | Password Reset - Password Update & NIST Validation | 1. User enters recovery session via email link. 2. Submits new password matching NIST policy and confirmation. | 1. Password hash updated in auth.users. 2. Parity check succeeds. 3. Returns HTTP 200 with redirect to /login?message=password_reset_success.
29 | Password Reset - Mandatory Global Revocation | 1. User updates password in browser A. 2. Attempt to make authenticated requests in browser B holding old session. | 1. Supabase executes signOut({ scope: 'global' }) upon password change. 2. Browser B session immediately rejected with HTTP 401. 3. Old refresh tokens completely dead.
MODULE 5: AUTH SECURITY, RATE LIMITING & SUSPENSION (SCRUM-60) — Assigned: junrilldisoy90
30 | Security - Login Brute Force Lockout | 1. Submit 5 consecutive invalid login attempts from same IP within 15 minutes. | 1. Attempt 6 rejected with HTTP 429 RATE_LIMIT_EXCEEDED. 2. Temporary IP cooldown enforced. 3. Rate limit warning displayed in UI toast.
31 | Security - Mid-Session Landlord Suspension | 1. Active landlord browsing /dashboard. 2. Admin sets profiles.is_suspended = true and triggers global sign-out. 3. Landlord clicks any action. | 1. Edge Middleware intercepts request. 2. Detects suspension flag. 3. Session immediately terminated. 4. Redirects to /login?error=account_suspended.
32 | Security - Concurrent Token Refresh Mutex Queue | 1. Trigger 5 simultaneous API calls as 1-hour JWT expires. | 1. Client-side mutex queue serializes refresh to single call. 2. 30s GoTrue leeway period honors inflight calls. 3. All 5 requests succeed without false revocation.
33 | Security - CSRF Origin Guard | 1. Submit state-changing authentication request with missing or mismatched origin header. | 1. Request rejected with HTTP 403 AUTH_CSRF_VALIDATION_FAILED. 2. Cookies remain untouched.
34 | Security - Transit Network Disconnect Simulation | 1. Trigger API request while network disconnects mid-flight. | 1. Client interceptor synthesizes AUTH_NETWORK_OFFLINE. 2. Local credentials preserved. 3. Non-blocking toast notifies user of offline state.
35 | Security - Open-Redirect Whitelist Enforcement | 1. Test redirect URLs against isSafeRedirectUrl(): - /search (relative) - https://evil.com (external) - //evil.com (protocol-relative) - /\evil.com (backslash) | 1. /search -> Allowed. 2. https://evil.com -> Blocked. 3. //evil.com -> Blocked. 4. /\evil.com -> Blocked. Fallback route /search or /login used.
36 | Security - Password Disparity Validation | 1. During password reset, submit 'newPassword' and mismatched 'confirmPassword'. | 1. Validation fails before network dispatch. 2. Field error: 'Passwords do not match.' 3. Zero API mutation calls executed.

## 1_REGISTRATION
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | USER REGISTRATION & ACTIVATION
| Test Description: |  | To validate user registration payloads, role whitelisting, NIST password complexity, Philippine mobile normalization, and PKCE email verification.
| TYPE OF TEST: |  | UT / IT
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
No | Test Classification | Test Steps: |  | Test Confirmation | Test Results
1 | Registration - Valid Renter | 1. Submit RegisterPayload with valid email, NIST-compliant password, role='renter', and phone '09171234567'. 2. Call registration Route Handler. |  | 1. HTTP 200/201 response. 2. Phone normalized to canonical +639171234567. 3. Profile row created in public.profiles via handle_new_user() trigger. 4. Verification email sent.
2 | Registration - Valid Landlord | 1. Submit RegisterPayload with role='landlord', valid credentials, and preferred landmark. 2. Execute registration Route Handler. |  | 1. User created with role='landlord'. 2. Response directs to /landlord/onboarding. 3. Landlord verification entity initialized.
3 | Registration - Anti-Privilege Escalation | 1. Submit payload attempting role='admin'. 2. Validate TypeScript contract, Route Handler validation, and database trigger. |  | 1. Contract rejects payload with INVALID_ROLE. 2. If bypassed via raw HTTP, server returns HTTP 403 PRIVILEGE_ESCALATION_ATTEMPT. 3. DB trigger enforces fallback to 'renter'.
4 | Registration - Weak Password Rejection | 1. Attempt registration with password < 8 chars ('Ab1!'). 2. Attempt password missing special character ('Password123'). 3. Attempt password exceeding 72 chars. |  | 1. Request rejected with HTTP 422 WEAK_PASSWORD. 2. Response details specify exact unmet NIST criteria. 3. Zero user records created.
5 | Registration - Invalid Philippine Phone | 1. Attempt registration with non-PH numbers (+1234567890, 08123456789, 12345). |  | 1. Validation fails with HTTP 422 INVALID_PHONE_NUMBER. 2. Field error explicitly requires 09XXXXXXXXX or +639XXXXXXXXX format.
6 | Registration - Duplicate Email Handling | 1. Submit registration payload using an existing email address (mika.cebu@example.com). |  | 1. Anti-enumeration defense preserves privacy. 2. Dispatches password reset notification to owner without revealing account collision to scraper.
7 | Registration - Turnstile Bot Defense | 1. Submit registration request with missing or invalid turnstileToken. |  | 1. Request immediately rejected with HTTP 400 CAPTCHA_VERIFICATION_FAILED. 2. Zero database queries executed.
8 | Email Verification - Valid PKCE Exchange | 1. User clicks confirmation link GET /auth/callback?code=VALID_CODE&type=signup. 2. Route Handler exchanges code via @supabase/ssr. |  | 1. auth.users.email_confirmed_at timestamp set. 2. Authenticated session cookies issued. 3. Redirects safely to /search (Renter) or /dashboard (Landlord).
9 | Email Verification - Expired Confirmation Code | 1. User clicks confirmation link after 24 hours (code=EXPIRED_CODE). |  | 1. Route Handler catches Supabase exchange error. 2. Redirects to /login?error=confirmation_expired. 3. UI displays persistent banner with resend CTA.
10 | Email Verification - Tampered PKCE Code | 1. Submit request with corrupted code code=INVALID_12345. |  | 1. Exchange fails. 2. Redirects to /login?error=invalid_confirmation_link. 3. Zero session cookies issued.
11 | Email Verification - Open-Redirect Defense | 1. User clicks link containing open-redirect injection: ?next=https://attacker-cebu.com. |  | 1. isSafeRedirectUrl() flags external protocol. 2. Destination sanitized and forced to default internal path (/search).

## 2_LOGIN
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | USER LOGIN & SESSION LIFECYCLE
| Test Description: |  | To check credential authentication, HTTP-only cookie issuance, Refresh Token Rotation (RTR), and suspended landlord lockout.
| TYPE OF TEST: |  | UT / IT
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
No | Test Classification | Test Steps: |  | Test Confirmation | Test Results
1 | Login - Valid Renter Login | 1. Submit valid Renter credentials (mika.cebu@example.com). 2. Execute login Route Handler. |  | 1. HTTP 200 response. 2. HTTP-only session cookies set (sb-*-auth-token, HttpOnly, Secure, SameSite=lax). 3. Redirect target resolved to /search.
2 | Login - Valid Landlord Login | 1. Submit valid Landlord credentials (carlos.landlord@example.com). |  | 1. HTTP 200 response. 2. Session cookies set. 3. Redirect target resolved to /dashboard.
3 | Login - Invalid Credentials | 1. Submit valid email with incorrect password. 2. Repeat 3 times. |  | 1. Request rejected with HTTP 401 AUTH_INVALID_CREDENTIALS. 2. Generic message: 'Invalid email or password.' 3. Zero cookies set.
4 | Login - Unconfirmed Email Block | 1. Attempt login using unconfirmed.renter@example.com. |  | 1. Request rejected with HTTP 403 AUTH_EMAIL_NOT_CONFIRMED. 2. UI instructs user to verify email before accessing account.
5 | Login - Suspended Account Block | 1. Attempt login with suspended landlord credentials (scammer.landlord@example.com). |  | 1. Authentication fails with HTTP 403 ACCOUNT_SUSPENDED. 2. Edge Middleware immediately blocks session creation. 3. UI directs user to support contact.
6 | Session - Cookie Chunking (>4096 Bytes) | 1. Authenticate user with extensive profile metadata triggering serialized cookie payload > 4KB. |  | 1. @supabase/ssr chunks session across sb-*-auth-token.0, sb-*-auth-token.1. 2. Middleware successfully reconstructs session. 3. Zero hydration drops.
7 | Session - Refresh Token Rotation (RTR) | 1. Present active refresh token to obtain fresh 1-hour JWT access token. |  | 1. New JWT issued. 2. Old refresh token invalidated; new single-use refresh token returned. 3. 30-second concurrency grace period active.
8 | Session - Token Reuse Detection & Lockout | 1. Malicious actor re-submits a previously rotated (revoked) refresh token. |  | 1. Supabase GoTrue flags token family reuse. 2. Entire token family instantly revoked. 3. All active sessions for user terminated. 4. HTTP 401 AUTH_REFRESH_TOKEN_REUSED emitted.

## 3_LOGOUT
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | USER SIGN-OUT & SESSION INVALIDATION
| Test Description: |  | To verify local and global device logout, cookie destruction, multi-tab broadcast synchronization, and router cache invalidation.
| TYPE OF TEST: |  | UT / IT / ST
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
No | Test Classification | Test Steps: |  | Test Confirmation | Test Results
1 | Logout - Local Device Sign-Out | 1. Authenticated user triggers Sign Out. 2. Execute signOutAction({ scope: 'local' }). |  | 1. Current session deleted in auth.sessions. 2. Set-Cookie emits Max-Age=0 and past epoch for all cookie chunks. 3. Remote sessions on other devices remain active.
2 | Logout - Global Multi-Device Sign-Out | 1. User selects 'Log out of all devices'. 2. Execute signOutAction({ scope: 'global' }). |  | 1. All rows for user_id purged from auth.sessions. 2. All refresh token families revoked. 3. All sessions across all devices terminated.
3 | Logout - Multi-Tab Broadcast Coordination | 1. User opens Tab A and Tab B while logged in. 2. User clicks Sign Out in Tab A. |  | 1. Tab A executes logout and posts SIGNED_OUT to BroadcastChannel('supabase.auth.token'). 2. Tab B receives message, purges local cache, and redirects to /login.
4 | Logout - Router Cache Purge & Back Button Guard | 1. User logs out from /dashboard. 2. User clicks browser 'Back' button. |  | 1. Next.js router.refresh() purges client cache. 2. Protected route headers (Cache-Control: no-store) force server re-evaluation. 3. Middleware blocks access with HTTP 307 to /login.
5 | Logout - Offline Sign-Out Fallback | 1. Disconnect network (navigator.onLine = false). 2. User triggers Sign Out. |  | 1. Optimistic local cookie destruction executes. 2. Memory credentials flushed. 3. UI navigates safely to unauthenticated state.

## 4_PASSWORD_RESET
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | PASSWORD RESET & RECOVERY
| Test Description: |  | To test self-service password recovery, single-use PKCE links, anti-enumeration neutrality, and mandatory session revocation upon password update.
| TYPE OF TEST: |  | UT / IT
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
No | Test Classification | Test Steps: |  | Test Confirmation | Test Results
1 | Password Reset - Valid Request | 1. Submit valid email to POST /api/auth/reset-password/request. |  | 1. HTTP 200 response. 2. Generic message: 'If an account is associated with this email, a recovery link has been dispatched.' 3. Single-use PKCE link sent.
2 | Password Reset - Anti-Enumeration Neutrality | 1. Submit unregistered email (nonexistent.user@example.com). |  | 1. HTTP 200 response. 2. Message and timing match valid request identically (artificial jitter applied). 3. Zero account existence disclosure.
3 | Password Reset - Rate Limiting | 1. Submit 4 password reset requests within a 15-minute rolling window for the same email. |  | 1. Requests 1–3 succeed. 2. Request 4 rejected with HTTP 429 AUTH_PASSWORD_RESET_RATE_LIMIT.
4 | Password Reset - Password Update & NIST Validation | 1. User enters recovery session via email link. 2. Submits new password matching NIST policy and confirmation. |  | 1. Password hash updated in auth.users. 2. Parity check succeeds. 3. Returns HTTP 200 with redirect to /login?message=password_reset_success.
5 | Password Reset - Mandatory Global Revocation | 1. User updates password in browser A. 2. Attempt to make authenticated requests in browser B holding old session. |  | 1. Supabase executes signOut({ scope: 'global' }) upon password change. 2. Browser B session immediately rejected with HTTP 401. 3. Old refresh tokens completely dead.

## 5_SECURITY_EDG
| Project Name: |  | AbangCebu AI (Metro Cebu Rental Discovery Platform)
| Module Name: |  | AUTH SECURITY, RATE LIMITING & SUSPENSION
| Test Description: |  | To verify brute force lockout, IP rate limits, mid-session landlord suspension, CSRF origin verification, and open-redirect sanitization.
| TYPE OF TEST: |  | ST (System & Security)
| Test Designed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | September 29, 2026
|  |  | END DATE: | October 2, 2026
| Test Executed by: |  | Jenny Villamor (QA Team)
|  |  | START DATE: | Pending Sprint 2
|  |  | END DATE: | Pending Sprint 2
No | Test Classification | Test Steps: |  | Test Confirmation | Test Results
1 | Security - Login Brute Force Lockout | 1. Submit 5 consecutive invalid login attempts from same IP within 15 minutes. |  | 1. Attempt 6 rejected with HTTP 429 RATE_LIMIT_EXCEEDED. 2. Temporary IP cooldown enforced. 3. Rate limit warning displayed in UI toast.
2 | Security - Mid-Session Landlord Suspension | 1. Active landlord browsing /dashboard. 2. Admin sets profiles.is_suspended = true and triggers global sign-out. 3. Landlord clicks any action. |  | 1. Edge Middleware intercepts request. 2. Detects suspension flag. 3. Session immediately terminated. 4. Redirects to /login?error=account_suspended.
3 | Security - Concurrent Token Refresh Mutex Queue | 1. Trigger 5 simultaneous API calls as 1-hour JWT expires. |  | 1. Client-side mutex queue serializes refresh to single call. 2. 30s GoTrue leeway period honors inflight calls. 3. All 5 requests succeed without false revocation.
4 | Security - CSRF Origin Guard | 1. Submit state-changing authentication request with missing or mismatched origin header. |  | 1. Request rejected with HTTP 403 AUTH_CSRF_VALIDATION_FAILED. 2. Cookies remain untouched.
5 | Security - Transit Network Disconnect Simulation | 1. Trigger API request while network disconnects mid-flight. |  | 1. Client interceptor synthesizes AUTH_NETWORK_OFFLINE. 2. Local credentials preserved. 3. Non-blocking toast notifies user of offline state.
6 | Security - Open-Redirect Whitelist Enforcement | 1. Test redirect URLs against isSafeRedirectUrl(): - /search (relative) - https://evil.com (external) - //evil.com (protocol-relative) - /\evil.com (backslash) |  | 1. /search -> Allowed. 2. https://evil.com -> Blocked. 3. //evil.com -> Blocked. 4. /\evil.com -> Blocked. Fallback route /search or /login used.
7 | Security - Password Disparity Validation | 1. During password reset, submit 'newPassword' and mismatched 'confirmPassword'. |  | 1. Validation fails before network dispatch. 2. Field error: 'Passwords do not match.' 3. Zero API mutation calls executed.